## onepagebusinesscase
Business Case Component | Sub-Component | Description | Key Data/Metrics | Status | Owner
**1. Executive Summary** |  | A concise overview and formal recommendation. | Expected ROI (5-year), Recommended Option Name | FALSE | Head of Strategy
1.1. Executive Summary | Business Needs Summary | A brief statement of the problem or opportunity being addressed. | Strategic Alignment Score, Problem Severity Index | FALSE | Head of Strategy
1.2. Executive Summary | Proposal & Recommendation | The core project proposal and formal recommendation to proceed. | Justification Rationale, Sponsor Approval Date (DD/MM/YYYY) | FALSE | Head of Strategy
**2. Reasons** |  | Why is the project necessary? (Problems/Opportunities) | Current system failure rate, Market growth percentage | FALSE | Business Analyst
2.1. Reasons | Context & Scope | Defines the boundaries and background of the business case. | Existing System Version, Project Boundary Description | FALSE | Business Analyst
2.2. Reasons | Alignment to Strategy | How the project supports organizational strategic objectives. | Supporting Strategic Goal ID, Percentage Contribution | FALSE | Business Analyst
**3. Business Options** |  | Analysis of options: Do Nothing, Do Minimum, Do Recommended. | Implementation Duration (Months), Total Cost Estimates (USD) | FALSE | Project Manager
3.1. Business Options | Do Nothing Option | Analysis of the costs and impacts of maintaining the status quo. | Cost of Inaction (Annual USD), Risk Exposure Rating | FALSE | Project Manager
3.2. Business Options | Do Minimum Option | Analysis of the least expensive, viable change option. | Minimum Viable Product Cost, Core Benefit Value | FALSE | Project Manager
3.3. Business Options | Recommended Option | Detailed description and justification for the chosen option. | Detailed Solution Summary [URL], Key Supplier Name | FALSE | Project Manager
**4. Expected Benefits** |  | What tangible and intangible benefits will the project deliver? | Annual cost savings (USD), Customer satisfaction increase (%) | FALSE | Benefits Manager
4.1. Expected Benefits | Quantitative Benefits | Measurable financial or efficiency improvements. | Process time reduction (Hours/Month), Expected Revenue Increase (%) | FALSE | Benefits Manager
4.2. Expected Benefits | Qualitative Benefits | Non-monetary advantages (e.g., morale, reputation). | Staff Morale Index, Brand Perception Change | FALSE | Benefits Manager
**5. Dis-benefits** |  | What negative impacts might occur? | Potential staff turnover (%), Temporary productivity dip (%) | FALSE | HR/Project Sponsor
**6. Timescale** |  | Key project phases and estimated duration. | Start Date (DD/MM/YYYY), End Date (DD/MM/YYYY) | FALSE | PMO
6.1. Timescale | Project Phases | Key stages with estimated duration and milestones. | Major Milestones Check, Phase 1 Completion Date | FALSE | PMO
6.2. Timescale | Resource Dependencies | Critical internal or external resource availability constraints. | Key Resource Name, Required Date | FALSE | PMO
**7. Costs** |  | Full cost breakdown (capital, resource, operational). | Total Capital Cost (USD), Annual Operating Cost (USD) | FALSE | Finance
7.1. Costs | Capital Expenditure | Investment costs for assets (e.g., hardware, software license). | Total CAPEX (USD), Software License Cost | FALSE | Finance
7.2. Costs | Operational Expenditure | Ongoing running and support costs (e.g., training, maintenance). | Annual OPEX (USD), Support Team FTE | FALSE | Finance
**8. Investment Appraisal** |  | Comparison of costs vs. benefits (e.g., ROI, NPV). | Net Present Value (NPV), Payback Period (Years) | FALSE | Financial Analyst
8.1. Investment Appraisal | Financial Metrics | Core financial measures used to evaluate the investment. | Internal Rate of Return (IRR), Return on Investment (ROI) | FALSE | Financial Analyst
8.2. Investment Appraisal | Sensitivity Analysis | How results change under different financial scenarios. | Worst Case NPV (USD), Expected Discount Rate (%) | FALSE | Financial Analyst
**9. Major Risks** |  | Summary of top risks and mitigation strategies. | Risk Probability (1-5), Risk Impact (1-5) | FALSE | Risk Manager
9.1. Major Risks | Identified Risks | Summary of top risks, their probability, and impact. | Top 3 Risk Names, Risk Mitigation Budget | FALSE | Risk Manager
9.2. Major Risks | Mitigation Strategy | High-level plan for responding to the major risks. | Contingency Reserve Amount (USD), Risk Management Plan [URL] | FALSE | Risk Manager

## risk log
Risk ID | Date Logged (DD/MM/YYYY) | Risk Category | Description (Cause -> Event -> Effect) | Probability (1-5) | Impact (1-5) | Proximity | Risk Owner | Response Type | Response Action/Contingency Plan | Status
R001 | 2025-10-15 | Technical | Legacy system failure -> Data loss -> Project delay. | 4 | 5 | Now | J. Smith | Reduce | Implement daily backup protocol. | TRUE
Column Name | Description | Example Data/Format
**Risk ID** | Unique identifier for tracking the risk event. | R001, R002, etc.
**Date Logged** | The date the risk was first identified and logged. | DD/MM/YYYY
**Risk Category** | Classification (e.g., Technical, Financial, External, People). | Technical
**Description** | Clear statement following the Cause $\rightarrow$ Event $\rightarrow$ Effect structure. | System failure $\rightarrow$ Loss of data $\rightarrow$ Delay
**Probability (1-5)** | Likelihood of the risk event occurring (1=Low, 5=High). | 3
**Impact (1-5)** | Severity of the effect if the risk occurs (1=Low, 5=High). | 4
**Proximity** | When the risk is expected to impact the project (Near, Medium, Far, Now). | Near
**Risk Owner** | Individual responsible for managing and monitoring the risk. | J. Smith
**Response Type** | Chosen strategy (Avoid, Reduce, Transfer, Accept, Share, Exploit, Enhance, Reject). | Reduce
**Response Action/Contingency Plan** | Specific actions to implement the response strategy or contingency. | Implement backup protocol
**Status** | Indicates if the risk is currently active (TRUE) or closed/retired (FALSE). | TRUE

## issue log
Issue ID | Date Raised (DD/MM/YYYY) | Issue Type | Description | Priority (1-5) | Severity (1-5) | Impact Assessment | Raised By | Actionee/Owner | Target Resolution Date | Status/Resolved
I-001 | 2025-11-26 | RFC | Request to integrate new reporting module not in initial scope. | 4 | 3 | Requires additional 40 hours of development and testing. | M. Davies | S. Patel | 2025-12-15 | FALSE
Column Name | Description | Example Data/Format
**Issue ID** | Unique identifier for tracking the specific issue. | I-001
**Date Raised (DD/MM/YYYY)** | The date the issue was formally recorded. | DD/MM/YYYY
**Issue Type** | Classification of the issue (RFC: Request For Change, OS: Off-Specification, P/C: Problem/Concern). | RFC
**Description** | Detailed explanation of the issue or problem encountered. | Hardware does not meet spec
**Priority (1-5)** | Importance of resolving the issue (1=Low, 5=High). | 4
**Severity (1-5)** | The degree of impact the issue has on the project objectives (1=Low, 5=High). | 5
**Impact Assessment** | Detailed analysis of the effect on time, cost, scope, and quality. | Requires additional budget
**Raised By** | Name of the individual who identified and logged the issue. | M. Davies
**Actionee/Owner** | Individual assigned responsibility for managing and resolving the issue. | S. Patel
**Target Resolution Date** | The planned date by which the issue should be resolved. | DD/MM/YYYY
**Status/Resolved** | Indicates if the issue is still Open/Active (FALSE) or Resolved/Closed (TRUE). | TRUE or FALSE

## highlight report
Section | Metric/Description | Last Period Value/Status | Current Value/Status | Deviation/Comment | Action Required (If Deviation Exists)
**1. Reporting Context** | Report Date/Period Covered | 19/11/2025 - 25/11/2025 | 26/11/2025 - 02/12/2025 | Next reporting period. | No action required
| Stage Title | Stage 2: Development | Stage 2: Development | No deviation | No action required
**2. Overall Status** | Project Health (RAG) | Green | Yellow | Risk R007 is now impacting scope. | Review Risk R007 mitigation effectiveness.
| Key Achievements This Period | Completed Module A design and testing. | Module B coding 50% complete. | Ahead of schedule on Module B. | No action required
| Planned Activities Next Period | Complete Module B coding and start user acceptance testing (UAT). | Start UAT preparations and address Issue I-002. | Focus shifts due to issue resolution. | Ensure resources are allocated to Issue I-002 resolution.
**3. Financial Status** | Actual Expenditure This Period | $15,000 | $16,500 | 10% over spend. | Investigate reasons for expenditure variance.
| Budget Forecast at Completion | $150,000 | $152,000 | Minor forecast increase due to I-001 request. | No action required
**4. Time Status** | Stage Completion Forecast | 2025-12-15 | 2025-12-17 | 2-day delay forecast due to resource conflicts. | Re-prioritize resources for critical path tasks.
| Overall Project Completion | 2026-02-28 | 2026-03-01 | 1-day overall slip.
**5. Issues & Risks** | Key Issues Raised/Resolved (I-001, I-003) | 2 raised, 1 resolved. | I-002 raised, I-003 resolved. | Active Issues = 4 | Require decision on I-001 (Request For Change).
| Key Risks (High Probability/Impact) | R007 (Scope Creep) | R007 is active and impacting. | Control response is failing. | Project Board needs to approve contingency plan for R007.
**6. Tolerance Status** | Stage Tolerance (Time) | Target: $\pm$ 5 Days | Forecast breach: 2 days delay. | Within tolerance. | Continue monitoring closely.
| Project Tolerance (Cost) | Target: $\pm$ $10,000 | Forecast deviation: $2,000. | Within tolerance. | No action required

## stage plan outline
Component/Section | Detail | Description/Definition (What/Why) | Metric/Target | Owner | Status/Checklist
**1. Stage Definition** | Objectives | Specific goals and measurable outcomes for this stage. | Stage Success Criteria Met | Project Manager | FALSE
| Scope & Exclusions | Clearly defined boundaries of the work to be performed. | Documented Scope Statement | Project Manager | FALSE
| Prerequisites/Assumptions | Conditions that must be true for the stage to start or proceed. | Validation Status | Project Manager | FALSE
**2. Products** | Products to be Created | List of all tangible outputs/deliverables from this stage. | Product Description [URL] | Team Manager | FALSE
| Quality Expectations | Standards and techniques for checking the quality of products. | Number of Quality Reviews | Project Assurance | FALSE
| Configuration Management | Plan for version control and storage of stage products. | CM Strategy Compliance | PMO | FALSE
**3. Activities & Schedule** | Work Breakdown Structure | Detailed breakdown of activities and Work Packages. | Activity ID/Parent ID | Team Manager | FALSE
| Time Estimates | Effort and duration estimates for each activity. | Total Stage Duration (Weeks) | Team Manager | FALSE
| Schedule Dependencies | Links between activities (internal and external). | Dependency ID/Link | Project Manager | FALSE
**4. Resources** | Human Resources | Required skills, roles, and person-days (FTE). | Total Person-Days Required | HR/Team Manager | FALSE
| Equipment & Materials | Specific tools, software, or machinery needed for this stage. | Acquisition Status | Team Manager | FALSE
**5. Financials** | Detailed Budget | Breakdown of CAPEX and OPEX for the stage activities. | Total Stage Budget (USD) | Finance | FALSE
| Expenditure Tracking | Method and frequency of cost monitoring. | Variance Threshold | Project Manager | FALSE
**6. Controls** | Stage Tolerances | Permissible deviation (Time, Cost, Scope, Quality, Benefit, Risk). | Cost: $\pm$ USD, Time: $\pm$ Days | Project Board | FALSE
| Reporting & Monitoring | Cycle and format for Highlight Reports and Checkpoint Reports. | Next Highlight Report Date | Project Manager | FALSE
**7. Risks & Issues** | Key Stage Risks | Identification of risks specific to executing this stage. | Risk ID/Mitigation Action | Risk Owner | FALSE
| Existing Issues | How current major issues will be handled during the stage. | Issue ID/Resolution Plan | Project Manager | FALSE

## lessons learned
Lesson ID | Date Raised (DD/MM/YYYY) | Source (e.g., QA, Team Review, Audit) | Lesson Category | Description of Event/Issue | Impact (Positive/Negative) | Recommendation/Action for Future Projects | Responsibility for Action | Status
LL-001 | 2025-11-15 | End-Stage Assessment | Planning | Underestimated duration for the UAT sign-off process. | Negative | Allocate an extra week for UAT sign-off. | PMO | FALSE
LL-002 | 2025-11-20 | Post-Project Review | Communications | Weekly status meetings were highly efficient and well-structured. | Positive | Use the same agenda template universally. | Head of Governance | FALSE
LL-003 | 2025-11-22 | Team Debrief | Technical | Vendor-supplied component required unexpected integration effort. | Negative | Mandate a proof-of-concept phase with all critical vendors. | Procurement/PM | FALSE
LL-004 | 2025-11-24 | Quality Audit | Quality | The early involvement of the Business Assurance team saved rework. | Positive | Incorporate Business Assurance earlier in Stage 1 planning. | Project Assurance | FALSE
LL-005 | 2025-11-25 | Team Debrief | Resources | Cross-training team members proved essential during staff leave. | Positive | Maintain mandatory cross-training sessions across all stages. | HR/Team Manager | FALSE
LL-006 | 2025-11-26 | Risk Review | Risk Management | Insufficient contingency budget was allocated for known high risks. | Negative | Increase standard risk contingency allocation by 5%. | Finance | FALSE